{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["龙城镇"],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"龙城镇","index":0,"n_rows":24,"n_cols":18,"rows_kept":24,"merged":[[0,0,0,17],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,1,12],[1,13,2,13],[1,14,2,14],[1,15,2,15],[1,16,2,16],[1,17,2,17]],"flags":["formulas_cached_only"]}
["萧县龙城镇2021年财政衔接推进乡村振兴补助资金项目计划完成情况明细表"]
["项目类别","项目名称","责任单位（主管部门）","实施单位和责任人","实施地点","建设任务和补助标准\n（批复建设内容）","实际完成情况","计划投资（万元）","其中：资金来源（万元）",{"$nulls":4},"实际使用资金（万元）","预定绩效目标","完成\n情况","预定减贫机制","实现\n情况"]
[{"$nulls":8},"中央\n衔接","省级\n衔接","市级\n衔接","县级\n衔接","其他资金"]
["一、基础设施建设扶贫工程"]
["（六）水毁修复工程"]
[null,"龙城镇水毁桥涵应急修复工程","县水利局","龙城镇\n张跃","龙城镇帽山村、人民村、刘行村、王大庄村","新建帽山村北山塘排洪沟桥和帽山村东山生产桥；拆除重建人民村东门桥、刘行村黄台2桥和3桥，拆除重建帽山村朱庄水塘排洪桥，王大庄村郭楼村水毁道路修复长100米、宽4米、厚18厘米","已完成",59.88,59.88,{"$nulls":4},48.932299,"损毁工程修复数量7处。改善脱贫户生产生活设施条件，提升村内基础设施水平","已完成","通过财政扶贫资金投入，改善农村基础设施条件，提升群众满意度","已实现"]
["二、产业脱贫工程"]
["（一）特色种养业奖补到户"]
[null,"龙城镇岱湖社区2021年特色种养业奖补到户项目","县农业农村局","龙城镇\n张跃","龙城镇\n岱湖社区","扶持6户脱贫户发展特色种养业","已完成",1.6,null,1.6,{"$nulls":3},1.4,"落实6户特色种养业奖补政策，增加脱贫户家庭收入","已完成","通过财政资金奖补，鼓励脱贫户发展特色产业，激发脱贫人口内生动力，增加家庭收入","已实现"]
[null,"龙城镇房庄社区2021年特色种养业奖补到户项目","县农业农村局","龙城镇\n张跃","龙城镇\n房庄社区","扶持8户脱贫户发展特色种养业","已完成",1.716,null,1.716,{"$nulls":3},1.716,"落实8户特色种养业奖补政策，增加脱贫户家庭收入","已完成","通过财政资金奖补，鼓励脱贫户发展特色产业，激发脱贫人口内生动力，增加家庭收入","已实现"]
[null,"龙城镇李台社区2021年特色种养业奖补到户项目","县农业农村局","龙城镇\n张跃","龙城镇\n李台社区","扶持1户脱贫户发展特色种养业","已完成",0.3,null,0.3,{"$nulls":3},0.3,"落实1户特色种养业奖补政策，增加脱贫户家庭收入","已完成","通过财政资金奖补，鼓励脱贫户发展特色产业，激发脱贫人口内生动力，增加家庭收入","已实现"]
[null,"龙城镇马楼村2021年特色种养业奖补到户项目","县农业农村局","龙城镇\n张跃","龙城镇\n马楼村","扶持6户脱贫户发展特色种养业","已完成",1.628,null,1.628,{"$nulls":3},1.628,"落实6户特色种养业奖补政策，增加脱贫户家庭收入","已完成","通过财政资金奖补，鼓励脱贫户发展特色产业，激发脱贫人口内生动力，增加家庭收入","已实现"]
[null,"龙城镇毛郢孜社区2021年特色种养业奖补到户项目","县农业农村局","龙城镇\n张跃","龙城镇\n毛郢孜社区","扶持6户脱贫户发展特色种养业","已完成",1.429,null,1.429,{"$nulls":3},1.429,"落实6户特色种养业奖补政策，增加脱贫户家庭收入","已完成","通过财政资金奖补，鼓励脱贫户发展特色产业，激发脱贫人口内生动力，增加家庭收入","已实现"]
[null,"龙城镇帽山村2021年特色种养业奖补到户项目","县农业农村局","龙城镇\n张跃","龙城镇\n帽山村","扶持23户脱贫户发展特色种养业","已完成",5.064,null,5.064,{"$nulls":3},4.764,"落实23户特色种养业奖补政策，增加脱贫户家庭收入","已完成","通过财政资金奖补，鼓励脱贫户发展特色产业，激发脱贫人口内生动力，增加家庭收入","已实现"]
[null,"龙城镇人民村2021年特色种养业奖补到户项目","县农业农村局","龙城镇\n张跃","龙城镇\n人民村","扶持12户脱贫户发展特色种养业","已完成",3.46,null,3.46,{"$nulls":3},3.46,"落实12户特色种养业奖补政策，增加脱贫户家庭收入","已完成","通过财政资金奖补，鼓励脱贫户发展特色产业，激发脱贫人口内生动力，增加家庭收入","已实现"]
[null,"龙城镇王大庄村2021年特色种养业奖补到户项目","县农业农村局","龙城镇\n张跃","龙城镇\n王大庄村","扶持28户脱贫户发展特色种养业","已完成",5.95,null,5.95,{"$nulls":3},5.95,"落实28户特色种养业奖补政策，增加脱贫户家庭收入","已完成","通过财政资金奖补，鼓励脱贫户发展特色产业，激发脱贫人口内生动力，增加家庭收入","已实现"]
["（二）特色产业发展"]
[null,"龙城镇房庄社区特色产业发展项目","县农业农村局","龙城镇\n张跃","龙城镇\n房庄社区","新建容积3600m³冷库及其配套设施","已完成",300,300,{"$nulls":4},211.146979,"项目建成投入运营后，预计年增加村集体收益不低于竣工决算金额的8%；收益量化、务工等预计带动86户脱贫户增收","已完成","通过扶贫资金投入，发展村级产业，壮大村集体经济，收益量化、开发村内公益岗位等形式带动脱贫户增收","已实现"]
["三、就业扶贫"]
[null,"基层辅助性公益岗位","县人社局","人社局\n吴伟","龙城镇","开发基层辅助性公益就业岗位47个","已完成",32.04,4.485600000000001,19.5444,8.01,null,null,32.04,"通过开发扶贫就业岗位，增加脱贫人口家庭收入","已完成","通过财政扶贫资金投入，提供就业岗位，拓宽脱贫人口就业渠道，带动增收","已实现"]
[null,"扶贫互助岗","县人社局","人社局\n吴伟","龙城镇","开发扶贫就业岗位","已完成",7.2,null,null,7.2,null,null,7.2,"通过开发就业岗位，增加脱贫人口家庭收入","已完成","通过财政资金投入，提供就业岗位，拓宽脱贫人口就业渠道，带动增收","已实现"]
[null,"脱贫劳动力外出务工交通补助项目","县人社局","人社局\n吴伟","龙城镇","对跨省就业的27名脱贫劳动力按300-500元不等的标准给予交通补助","已完成",1.32,null,1.32,{"$nulls":3},1.32,"计划2021年底前补助脱贫劳动者交通补助27人","已完成","以提供交通补助的形式，激发脱贫户内生动力","已实现"]
["五、教育项目"]
[null,"雨露计划","县教体局","教体局\n杜尚训","龙城镇","向符合条件的脱贫家庭安排“雨露计划”补助90人次","已完成",13.5,13.5,{"$nulls":4},13.5,"为建档立卡贫困家庭中职高职学生进行补助，减轻脱贫户家庭子女教育负担","已完成","以教育补贴的形式，减轻贫困家庭教育支出负担","已实现"]