{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["永堌镇"],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"永堌镇","index":0,"n_rows":29,"n_cols":29,"rows_kept":29,"merged":[[0,1,0,28],[1,0,4,0],[1,1,4,1],[1,2,4,2],[1,3,4,3],[1,4,4,4],[1,5,4,5],[1,6,3,8],[1,9,4,9],[1,10,4,10],[1,11,4,11],[1,12,2,13],[1,14,4,14],[1,15,1,26],[1,27,4,27],[1,28,4,28],[2,15,3,18],[2,19,2,25],[2,26,4,26],[3,12,4,12],[3,13,4,13],[3,19,3,21],[3,22,3,23],[3,24,4,24],[3,25,4,25]],"flags":["formulas_cached_only"]}
[null,"萧县永堌镇2023年巩固拓展脱贫攻坚成果和乡村振兴项目库"]
["序号","项目类别","项目名称","建设\n性质","主管部门","实施单位和责任人","项目实施地点",null,null,"建设任务（内容及规模）","时间进度\n(完成时限）","预计投资","其中：",null,"项目年度总目标","绩效目标",{"$nulls":11},"群众参与","联农带农机制（土地流转、就业务工、带动生产、帮助产销对接、资产入股、收益分红...）"]
[{"$nulls":15},"产出指标",{"$nulls":3},"效益指标",{"$nulls":6},"满意度指标（受益人口满意度）"]
[{"$nulls":12},"财政资金","其他资金",{"$nulls":5},"经济效益指标",null,null,"社会效益指标",null,"生态效益指标","可持续影响指标"]
[{"$nulls":6},"乡镇","行政村","是否\n出列村",{"$nulls":6},"数量指标","质量指标（验收合格率）","时效指标（完工及时率）","成本指标","带动脱贫户经济总收入","资产股权年收益率","受益劳动者经济总收入","受益户数","受益人数"]
[null,"一、产业发展"]
[null,"（一）生产项目"]
[1,"生产项目（种植/养殖业）","2023年永堌镇前进村特色种养殖补贴到户项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","前进村","是","扶持50户脱贫户（含监测对象）发展特色种养业","2023年12月15日前",6.752,6.752,null,"扶持50户脱贫户发展特色种养业，鼓励其扩大种养殖规模。","大棚蔬菜种植面积2亩、杏树28.8亩，羊养殖数量398只、牛15头、猪3头；",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/",8.44,"/\n","/\n",50,115,"/","/","≥95%","参与项目申报、实施过程监督、完成后受益","以产业补助的形式对脱贫户进行补助，鼓励发展特色产业，激发脱贫人口内生动力，扩大种养殖规模，增加脱贫户收入"]
[2,"生产项目（种植/养殖业）","2023年永堌镇胜利村特色种养殖补贴到户项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","胜利村","否","扶持49户脱贫户（含监测对象）发展特色种养业","2023年12月15日前",4.786,4.786,null,"扶持49户脱贫户发展特色种养业，鼓励其扩大种养殖规模。","葡萄种植面积64.9亩、杏树12亩、梨2.5亩，羊养殖数量46只、牛2头、猪8头、蜜蜂15箱、鸡300只；",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/",5.9825,"/\n","/\n",49,94,"/","/","≥95%","参与项目申报、实施过程监督、完成后受益","以产业补助的形式对脱贫户进行补助，鼓励发展特色产业，激发脱贫人口内生动力，扩大种养殖规模，增加脱贫户收入"]
[3,"生产项目（种植/养殖业）","2023年永堌镇许岗村特色种养殖补贴到户项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","许岗村","否","扶持12户脱贫户（含监测对象）发展特色种养业","2023年12月15日前",1.5,1.5,null,"扶持12户脱贫户发展特色种养业，鼓励其扩大种养殖规模。","杏树种植面积10亩，羊养殖数量50只、猪5头；",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/",1.875,"/\n","/\n",12,25,"/","/","≥95%","参与项目申报、实施过程监督、完成后受益","以产业补助的形式对脱贫户进行补助，鼓励发展特色产业，激发脱贫人口内生动力，扩大种养殖规模，增加脱贫户收入"]
[4,"生产项目（种植/养殖业）","2023年永堌镇山窝村特色种养殖补贴到户项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","山窝村","否","扶持21户脱贫户（含监测对象）发展特色种养业","2023年12月15日前",2.368,2.368,null,"扶持21户脱贫户发展特色种养业，鼓励其扩大种养殖规模。","葡萄种植面积5.2亩、杏树18.5亩、豌豆5亩，羊养殖数量79只、蜜蜂15箱；",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/",2.96,"/\n","/\n",21,38,"/","/","≥95%","参与项目申报、实施过程监督、完成后受益","以产业补助的形式对脱贫户进行补助，鼓励发展特色产业，激发脱贫人口内生动力，扩大种养殖规模，增加脱贫户收入"]
[5,"生产项目（种植/养殖业）","2023年永堌镇窦庄村特色种养殖补贴到户项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","窦庄村","是","扶持48户脱贫户（含监测对象）发展特色种养业","2023年12月15日前",5.079,5.079,null,"扶持48户脱贫户发展特色种养业，鼓励其扩大种养殖规模。","大棚蔬菜种植面积4亩、梨5.4亩，大棚葡萄6亩、葡萄47亩、露地蔬菜4.6亩、洋葱2亩，羊养殖数量98只、猪30头、牛33头、精养 鱼塘18亩；",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/",6.34875,"/\n","/\n",48,100,"/","/","≥95%","参与项目申报、实施过程监督、完成后受益","以产业补助的形式对脱贫户进行补助，鼓励发展特色产业，激发脱贫人口内生动力，扩大种养殖规模，增加脱贫户收入"]
[6,"生产项目（种植/养殖业）","2023年永堌镇马庄村特色种养殖补贴到户项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","马庄村","否","扶持28户脱贫户（含监测对象）发展特色种养业","2023年12月15日前",3.58,3.58,null,"扶持28户脱贫户发展特色种养业，鼓励其扩大种养殖规模。","洋葱种植面积12亩，羊养殖数量196只、猪22头；",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/",4.475,"/\n","/\n",28,79,"/","/","≥95%","参与项目申报、实施过程监督、完成后受益","以产业补助的形式对脱贫户进行补助，鼓励发展特色产业，激发脱贫人口内生动力，扩大种养殖规模，增加脱贫户收入"]
[7,"生产项目（种植/养殖业）","2023年永堌镇吴庄村特色种养殖补贴到户项目",null,"县农业农村局","永堌镇\n任精芳","永堌镇","吴庄村","是","扶持22户脱贫户（含监测对象）发展特色种养业","2023年12月15日前",2.455,2.455,null,"扶持22户脱贫户发展特色种养业，鼓励其扩大种养殖规模。","大棚蔬菜种植面积11亩、大棚葡萄2亩、梨树9.6亩、洋葱11.3亩，羊养殖数量38只、猪4头；",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/",3.06875,"/\n","/\n",22,46,"/","/","≥95%","参与项目申报、实施过程监督、完成后受益","以产业补助的形式对脱贫户进行补助，鼓励发展特色产业，激发脱贫人口内生动力，扩大种养殖规模，增加脱贫户收入"]
[null,"（二）生产/加工流通等"]
[1,"生产项目（休闲农业与乡村旅游）","梅花谷基础设施建设项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","王山窝村","否","修建梅园道路修建及配套设施（梅园上段新建水泥路，长650米、宽5米、厚0.2米；加宽梅园路中段水泥路，长450米、宽1米、厚0.3米；加宽梅园路下段，通过在路旁排水沟的位置上砌石建桥加宽路面，沟长140米、宽4米）；园内修建便民服务点，面积约119平方米；修缮老房屋院落7套，房屋约2631平方米及配套设施","2023年12月15日前",499.4,499.4,null,"修建梅园道路修建及配套设施（梅园上段新建水泥路，长650米、宽5米、厚0.2米；加宽梅园路中段水泥路，长450米、宽1米、厚0.3米；加宽梅园路下段，通过在路旁排水沟的位置上砌石建桥加宽路面，沟长140米、宽4米）；园内修建便民服务点，面积约119平方米；修缮老房屋院落7套，房屋约2631平方米及配套设施，带动脱贫人口（含监测帮扶对象）及一般农户发展增收，增加村集体经济收入。","梅园上段新建水泥路，长650米；加宽梅园路中段水泥路，长450米；\n修缮老房屋院落7套，房屋约2631平方米",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/",null,"/",null,334,1535,null,null,"≥95%","参与项目申报、实施过程监督和建成后受益","以就业务工、帮助产销对接等方式促进脱贫人口（含监测帮扶对象）及一般农户发展增收，同时增加村集体收入"]
[null,"三、乡村建设行动"]
[null,"（一）农村基础设施"]
[1,"\n农村基础设施（含产业配套基础设施）\n农村道路建设（通村路、通户路、小型桥梁等）\n","拆除重建窦庄桥","改建","县水利局","县水利局\n张勋","永堌镇","窦庄村","是","重建桥涵1座，跨数、跨度、桥面宽为1m*6m*6m。","2023年12月15日前",40,40,null,"重建桥涵1座，改善群众生产生活设施条件","拆除重建桥涵1座",{"v":1,"d":"100%"},{"v":1,"d":"100%"},{"$nulls":4},1238,3830,null,null,"≥95%","参与项目申报、实施过程监督、竣工后受益","以小型农田水利设施建设的形式，改善产业基础设施条件，助力产业发展"]
[2,"\n农村基础设施（含产业配套基础设施）\n农村道路建设（通村路、通户路、小型桥梁等）\n","农村公路养护工程朝张路","改建","县交通运输局","县交通运输局\n胡传伦","永堌镇","前进村","是","修复安防设施等","2023年12月15日前",35,null,35,"通过对已建成道路开展维修养护，提升道路通行能力，改善脱贫人口生产生活设施条件","养护里程约19.928公里",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/","/","/","/",350,1300,null,null,"≥95%","完善农村基础设施建设条件，提升群众满意度","以改基础设施的形式，带动群众务工并增加收入，为群众长久可持续发展提供便利"]
[3,"\n农村基础设施（含产业配套基础设施）\n农村道路建设（通村路、通户路、小型桥梁等）\n","永堌镇“进村入户”道路商砼、石子采购项目","改建","县交通运输局","永堌镇\n任精芳","永堌镇","胜利、王山窝、窦庄、许岗子村","/","采购商砼约9037立方米、石子约3012方用于进村入户道路改建","2023年12月15日前",500,500,null,"建设道路长约23.8公里，改善脱贫人口生产生活设施条件，提升村内基础设施水平","采购商砼约9037立方米、石子约3012方用于进村入户道路改建",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/","/","/","/",2024,6326,null,null,"≥95%","项目申报、实施过程务工和监督、竣工后受益","以道路建设的形式，改善村内基础设施条件，提升脱贫人口出行水平"]
[4,"\n农村基础设施（含产业配套基础设施）\n农村道路建设（通村路、通户路、小型桥梁等）\n","永堌镇王山窝自然村道路建设项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","王山窝村","否","新建村内主干道及入户路共3500米，宽度3.5米、厚度18厘米。","2023年12月15日前",140,140,null,"新建村内主干道及入户路共3500米，改善农户生产生活设施条件，提升村内基础设施水平","新建村内主干道及入户路共3500米",{"v":1,"d":"100%"},{"v":1,"d":"100%"},null,"/","/","/",246,913,null,null,"≥95%","项目申报、实施过程监督、竣工后项目所在地受益","以道路建设的形式，为贫困户长久可持续发展提供便利"]
[null,"（二）人居环境整治"]
[1,"人居环境整治（农村污水治理）","萧县农村黑臭水体综合整治项目","新建","县生态环境分局","永堌镇\n任精芳","永堌镇","许岗村","否","1处农村黑臭水体综合整治，包括清漂浮物、截污治污、道路修复等。","2023年12月15日前",600,600,null,"完成1处农村黑臭水体综合整治，包括清漂浮物、截污治污、道路修复等。有效提升农村人居环境","建设5千米左右污水管道，消除1处农村黑臭水体隐患治理，有效提升农村人居环境",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/","/","/","/",512,1850,null,null,"≥95%","项目申报、实施过程监督、竣工后项目所在地受益","改善村内基础设施条件，提升脱贫人口生活设施水平"]
[2,"人居环境整治（农村污水治理）","萧县农村黑臭水体综合整治项目","新建","县生态环境分局","永堌镇\n任精芳","永堌镇","胜利村","否","1处农村黑臭水体综合整治，包括清淤、岸坡整治、截污治污等。","2023年12月15日前",40,40,null,"完成1处农村黑臭水体综合整治，包括清淤、岸坡整治、截污治污等。有效提升农村人居环境","完成1处农村黑臭水体治理，有效提升农村人居环境",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/","/","/","/",294,1530,null,null,"≥95%","项目申报、实施过程监督、竣工后项目所在地受益","改善村内基础设施条件，提升脱贫人口生活设施水平"]
[3,"人居环境整治（农村污水治理）","萧县农村黑臭水体综合整治项目","新建","县生态环境分局","永堌镇\n任精芳","永堌镇","窦庄村","是","1处农村黑臭水体综合整治，包括清淤、岸坡整治、截污治污、桥梁修复、青苗树木补偿等。","2023年12月15日前",500,500,null,"完成1处农村黑臭水体综合整治，包括清淤、岸坡整治、截污治污、桥梁修复、青苗树木补偿等。有效提升农村人居环境","完成1处农村黑臭水体治理，有效提升农村人居环境",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/","/","/","/",930,1670,null,null,"≥95%","项目申报、实施过程监督、竣工后项目所在地受益","改善村内基础设施条件，提升脱贫人口生活设施水平"]
[4,"人居环境整治（农村污水治理）","永堌镇王山窝自然村雨污水管网建设项目","新建","县农业农村局","永堌镇\n任精芳","永堌镇","王山窝村","否","新建雨污水管网1300米；接户管网3300米","2023年12月15日前",280,280,null,"新建雨污水管网1300米；接户管网3300米，改善农户生产生活设施条件，提升村内基础设施水平。","新建雨污水管网1300米；接户管网3300米",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/","/","/","/",{"v":133.333333333333,"d":"133"},{"v":469.333333333333,"d":"469"},null,null,"≥95%","项目申报、实施过程监督、竣工后受益","改善村内基础设施条件，提升脱贫人口生活设施水平"]
[null,"（一）村容村貌提升"]
[null,null,"永堌镇王山窝村王山窝自然村坑塘治理项目","改建","县农业农村局","永堌镇\n任精芳","永堌镇","王山窝村","否","对村内1000平方米河沟坑塘进行整治，包括疏浚清淤、岸坡整治等。","2023年12月15日前",20,20,null,"对村内1000平方米河沟坑塘进行整治，改善农户生产生活设施条件，提升村内人居环境","村内1000平方米河沟坑塘进行整治",{"v":1,"d":"100%"},{"v":1,"d":"100%"},"/","/","/","/",328,1010,null,null,"≥95%","项目申报、实施过程监督、竣工后受益","以坑塘全面整治的形式，改善脱贫人口、监测对象及一般农户生活设施条件，提升农村人居环境"]